## Sheet1
Project Timeline - ByteMentor
KW | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
SW | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Topics
Define project scope, objectives, requirements | [16 empty] | Milestone 1 | Complete data collection, preprocessing, and annotation.
Identify academic resources and data sources | [16 empty] | Milestone 2 | Train and validate the model.
Research AI tools and libraries |  |  |  | 1 | [12 empty] | Milestone 3 | Conduct testing and fine tuning.
Structure the data | [16 empty] | Milestone 4 | Finalize the LLM and the project.
Text cleaning, annotation, categorization | [16 empty] | Moonshot | Deploy it to the whole class.
Labeling
Split into train and test data
LLM selection
Set up training enviroment
Define fine-tuning parameters
Train the model
Model refinement | [9 empty] | 2
Conduct accuracy tests | [11 empty] | 3
UI Development
Bug fixes and evaluation | [13 empty] | 4
Github Page & Blog post
5
Proposal Presentation
Midterm Presentation
Final Presentation